# JISC DEVELOPMENT PROGRAMMES

# Project Document Cover Sheet

# PROGRESS REPORT Sep 2005 – Aug 2006

# Project

| Project Acronym | ESP-GRID | Project ID |  |
| --- | --- | --- | --- |
| Project Title | Evaluation of Shibboleth and PKI for Grids |  |  |
| Start Date | 1 July 2004 | End Date | 31 Mar 2006 (extended) |
| Lead Institution | Oxford University |  |  |
| Project Director | Professor Paul Jeffreys / Mr Matthew Dovey |  |  |
| Project Manager & contact details | Dr Mark Norman Research Technologies Service, Oxford University Computing Services 13 Banbury Road Oxford OX2 6NN Email: mark.norman@oucs.ox.ac.uk Tel: 01865 273287 Fax: 01865 273275 |  |  |
| Partner Institutions | None |  |  |
| Project Web URL | http://wiki.oucs.ox.ac.uk/esp-grid/ |  |  |
| Programme Name (and number) | Core Middleware: Technology Development |  |  |
| Programme Manager | Nicole Harris |  |  |

# Document

| Document Title | Progress Report |  |  |
| --- | --- | --- | --- |
| Reporting Period | Sept 2005 – Aug 2006 |  |  |
| Author(s) & project role | Mark Norman (Project Manager) |  |  |
| Date | 18 October 2006 | Filename | ESPGRID_ProgressReport_Aug06.pdf |
| URL |  |  |  |
| ##### Access |  Project and JISC internal |  |  General dissemination |

# Document History

| Version | Date | Comments |
| --- | --- | --- |
| 1.0 | 2 Sept 05 | Feedback from Alun – and final version produced. |
| 0.1 | 1 Sept 05 | Draft version for checking and comments from Alun. |

# Overview of Project

### Grant Statement

[Please confirm that the project is being conducted under the terms agreed with JISC in the letter of grant and the JISC Terms and Conditions attached to it.

Note any changes to the original award, including any extensions or alterations granted.]

I can confirm that the project is being conducted in accordance with the terms agreed in the letter of grant.

### 2. Aims and Objectives

[Explain any changes to the original aims/objectives outlined in the project plan.

List the targets set for this reporting period and explain if they have been met.]

The targets set for this reporting period are as presented in the table below.  The main achievements and any remaining expected due dates are as presented in the table below.

| Target/milestone for reporting period | Delivery due date |  | Complet-ion date | URL (http://wiki.oucs.ox.ac.uk/esp-grid/ plus…) |
| --- | --- | --- | --- | --- |
| (WP2) Evaluation |  |  |  |  |
|  |  |  |  | See: EvaluationPages |
| Against aims and obj.s | End proj. |  | Aug 06 | EvalAgainstObjectives |
| Against BRIDGES project | End proj. |  | Aug 06 | EvalAgainstObjectives |
| Against CM Programme | End proj. |  | Aug 06 | EvalAgainstObjectives |
| Evaluating exp. etc. of Developers | End proj. |  | June 06 | DeveloperEvaluation |
| Ditto – Users | End proj. |  | June 06 | UserPerspective |
| Ditto – Service Providers | End proj. |  | June 06 | ServiceProvidersEvaluation |
| (WP3) Dissemination |  |  |  |  |
| Consultation on functional requirements report | Aug 05 |  | Nov 05 | GridRequirements |
| Consultation on PKI evaluation report | Sept 05 |  | Dec 05 | ShibPKIEvaluation |
| Consultation on Shibboleth and grids report | Oct 05 |  | Dec 05 | ShibPKIEvaluation |
| Policy management consultation | July 05 |  | Dec 05 | PolicyManagement |
| Grid/Shib prototypes | Nov 05 |  | Feb 06 | NeSC_Shibbolized_Resources |
| VO work | Unplanned |  | April 06 | VODefinition |
| ‘Road map’ document | Jan 07 |  |  | In late draft at Final_recommendations_for_e-Science |
| (WP4) Grid Architecture Overview |  |  |  |  |
|  | Sept 05 |  | Sept 05 | RequirementsDoc See also: RequirementsBibliography |
| (WP5) PKI Evaluation |  |  |  |  |
|  | May 05 |  | Dec 05 | ShibPKIEvaluation |
| (WP6) Shibboleth Evaluation |  |  |  |  |
|  | Sept 05 |  | Dec 05 | ShibPKIEvaluation |
| (WP7) Policy Management |  |  |  |  |
|  |  |  | May 06 | PolicyManagement |
| (WP8) Grid Prototype |  |  |  |  |
|  |  | Feb 06 | Feb 06 | NeSC_Shibbolized_Resources |
| (WP9) Grid integration/Migration |  |  |  |  |
|  | Mar 06 |  | Jan 07 | In late draft at Final_recommendations_for_e-Science |

### 3. Overall Approach

[Explain any changes to the overall approach outlined in the project plan.]

As described in previous reports, some of the outputs of the earlier work packages were delayed, partly due to the situation of work package four being more difficult, and partly due to loss of staff to the project.  The overall effect was to delay the final documents but those documents generally reached ‘good draft’ stage not long after their initial due date.

We have also proposed that a small (no cost) follow-up project be initiated in order to test some of the use-cases and look into some usability issues arising from the project.  This has been accepted and the project is now under way and is expected to complete in January 2007.  (See section 5 below for more details).

### 4. Project Outputs

[Summarise progress during the reporting period and milestones/deliverables achieved.]

During this reporting period, most of the remaining milestones of the total project have been achieved.  These outputs are available on line at http://wiki.oucs.ox.ac.uk/esp-grid/.

### 5. Project Outcomes

[Summarise achievement against objectives, list outcomes and findings to date, and any interim conclusions.]

The objective of work package four (Grid Architecture Overview) was the “production of an overview of functional requirements specification for grid authentication and authorisation informed by the UK e-Science community (with bibliography of relevant documents).  This was achieved (eventually) in full.

The objective of work packages five and six (PKI Evaluation and Shibboleth Evaluation) were “a critical evaluation of how components of PKI fit within a grid infrastructure” and “a critical evaluation of how components of Shibboleth fit within grid infrastructure”, respectively.  We found that it was most convenient to combine these two work packages and the objectives were achieved in full.

Work package seven was modified early in the project, but this turned out to be a major unexpected outcome of ESP-GRID.  A survey of policy management tools and techniques was undertaken, and the developers of each of the tools were asked for their feedback.  This resulted in a resource that should be of great utility for grid and information environment researchers and developers for the medium term.  Initially it was difficult separating the aims of development projects from the reality of what the current versions of their tools delivered.  However this work helped to establish the current state of play and was very well received.

As discussed in our previous interim report, work package eight (Grid Prototype) was out-sourced to the NeSC team at the University of Glasgow.  This work went well and helped to inform this team of many issues surrounding the deployment of Shibboleth with Grids.  The NeSC team also produced much ‘cook-book’ like documentation which may be of interest to the community.  These have been added to their general output at http://labserv.nesc.gla.ac.uk/projects/etf/.

The objectives of the Grid integration/Migration work package (9) were less clear as we could not predict the exact nature of the prototype arising from work package eight.  It was initially envisaged that a ‘Road map’ integration or migration document would be produced at the end of the project. Part of the essence of the project was that we were to keep an open mind regarding the eventual architecture that we would build, prototype or recommend. With our rather - some would say - simplistic approach of a Customer-Service Provider model of grid use benefiting the vast majority of grid users, and the applicability of Shibboleth therein, a 'Road map' seemed inappropriate. We are not recommending a 'migration' and the 'integration' is straightforward. Nevertheless, the project is establishing some recommendations for the UK e-Science community and these are in good draft form at http://wiki.oucs.ox.ac.uk/esp-grid/Final_recommendations_for_e-Science.

[How do you see the project developing?  Has progress changed the project in any way, and are there implications for the programme?]

A notable outcome of the project is the formation of a small follow up that is focussing on usability and the types of users in a future grid.  This is to be pursued using the under-spend accrued during the project and accounts for the final extension to January 2007.  This mini-project is entitled ‘Barriers to Initial Involvement for Novice Grid Users’ and is detailed at 
http://wiki.oucs.ox.ac.uk/esp-grid/JISC_Proposal_for_Phase_2.

[What lessons have been learned that could be passed on to other projects or applied elsewhere?]

### 6. Stakeholder Analysis

[Summarise the project’s engagement with stakeholders including users.]

- the project has continued to engage with the ‘Shib and Grid BOF’ at GGF/OGF (see http://www.federation.org.au/cgi-bin/mailman/listinfo/shibgrid-bof and, e.g., http://www.ggf.org/documents/GFD.79.pdf)

- the project took part in a Usability in e-Science Workshop at the National e-Science Centre over January 26-27, 2006 (see http://www.nesc.ac.uk/esi/events/613/scheduleUWS06.pdf) and we prepared a paper for this event – see http://wiki.oucs.ox.ac.uk/esp-grid/UsabilityWorkshopNeSC - that was a precursor to the two papers submitted – and accepted – for the All Hands Meeting 2006).  This was a good opportunity to talk about security and usability to this community.

- the project has been represented at various UK e-Science and JISC meetings.

### 7. Risk Analysis

[Summarise any problems that have occurred and any mitigating actions taken.]

Much re-scheduling took place but, as noted in section three, above, many of the outputs were substantively completed by their planned delivery dates.  The final versions were a little delayed due to the extra work involved in obtaining technical feedback (as much of the local technical input had been removed).

### 8. Standards

[Note any changes in the standards to be used and the reasons.]

Nothing to report.

### 9. Technical Development

[Note any changes in the development approach or technologies to be used and the reasons.]

No changes to report.

### 10. Intellectual Property Rights

[Summarise progress clearing any third-party rights.]

Nothing to report.

## Project Resources

### 11. Project Partners

[Explain any changes to the institutional project partners or subcontractors, and any impacts this has/will have on the project or schedule.

What other institutions or organisations are you or do you plan to collaborate with?]

As mentioned above, the project formed a partnership with the University of Glasgow National e-Science Centre and, in particular, Dr Richard Sinnott and many of the researchers based at the NeSC@Glasgow.

### 12. Project Management

[Note any changes in project staff or their roles since the last report.  Briefly explain any problems or gaps with staffing and the effect this has had on the project schedule.]

No changes.

### 13. Programme Support

[Summarise contact with/influence of the programme, e.g. with the programme manager, formal or informal links with other projects, or programme-related activities.

What further support would you like from the programme, e.g. guidance, workshops, etc?

Do you have any suggestions for improving the programme?]

The project continues to have good support from the programme management.

### 14. Budget

Use the budget template to report expenditure against and attach as Appendix A.  Explain the reasons for any significant overspend or underspend.

See Appendix A.

## Detailed Project Planning

### 15. Workpackages

[Report progress against plan, noting key activities during the reporting period.  Explain why any targets haven’t been met.

List objectives for the next reporting period, note if any changes to plan are needed, and explain why.]

Section 2 gives the dates when the outputs were completed and further details are given in Section 5.  The project is substantially finished  As noted at the end of Section 5 a small-scale follow up is under way now to look at some usability aspects, especially regarding new users.  This should be a no-cost follow up, but will extend the project until the end of January 2007.  Full details can be found at http://wiki.oucs.ox.ac.uk/esp-grid/JISC_Proposal_for_Phase_2.

### 16. Evaluation Plan

Report progress against plan, and note any evaluation results during the reporting period.

List objectives for the next reporting period, note if any changes to plan are needed, and explain why.

A self-led evaluation has taken place and may be found at
http://wiki.oucs.ox.ac.uk/esp-grid/EvaluationPages.

### 17. Quality Assurance Plan

Report progress against plan, describe the QA procedures put in place, and any QA results during the reporting period.

List objectives for the next reporting period, note if any changes to plan are needed, and explain why.

As development took place at the University of Glasgow, this activity was carried out using procedures local to the development team.  The work has been demonstrated at meetings many times and was inspected by Curtis and Cartwright in July and August of this year (both at Oxford and Glasgow).

### 18. Dissemination Plan

Report progress against plan, noting dissemination done, whether you feel it was successful, and any publicity the project received during the reporting period.

List objectives for the next reporting period, note if any changes to plan are needed, and explain why.

The main dissemination activity for us has been through GGF meetings and the two papers [to be] presented at the UK e-Science All Hands meetings in September.  See http://wiki.oucs.ox.ac.uk/esp-grid/AllHandsPapers2006 for further details.

### 19. Exit/Sustainability Plan

Report progress against plan, noting any issues related to archiving, preservation, maintenance, supporting documentation, etc.

####

List objectives for the next reporting period, note if any changes to plan are needed, and explain why.

The main operational outputs of the project appeared at NESC@Glasgow as the Shibboleth component of their portalised access to BRIDGES, VOTES and DyVOSE.  These components will still be used after the project is over.  Our small follow-up project (as mentioned in sections 5 and 15, above) should also help to establish some of the concepts of Service End Users and Service Providers for grids, that we developed as part of the requirements gathering stages.

As part of the sustainability of the ESP-GRID project, we have continued to influence the ShibGrid project.  The ShibGrid project is aimed at what we would express as Power Users, but it is clear that some less computing-technical users may benefit from the use cases that hide the certificates from the users.  Nevertheless, we have some reservations about mixing Shibboleth and X.509 in this way.

The findings of the project may also influence campus grid developments at Oxford with our emphasis on usability.  Currently, the campus grid favours Power Users heavily but this may change.

## Appendix A.  Project Budget

The budget reports expenditure for financial years one, two and three (July 2004-July 2006).  Balances are presented as carrying over from year to year.

|  | YR1 Budget | YR1 Actual | YR 2 br. fw | YR 2 budget | YR 2 Actual | YR 3 br. fw | YR3 Budget | YR 3 Actual | YR 3 Balance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | July 04 |  |  | July 05 |  |  | July 06 |  |
| Staff costs | 994.00 |  | 994.00 | 57,798 | 41,057.69 | 17,734.31 | 66,265 | 74,614.91 | 9,384.40 |
| (incl. outsourc) |  |  |  |  |  |  |  | (33,970.23) |  |
| Travel/Subsist. | 200 |  | 200 | 2,000 | 116.26 | 2,107.74 | 500 | 2,456.70 | 151.04 |
| Equipment (items over £10k) | 8,000 |  | 8,000 | 1,000 | 2,587.92 | 6,412.08 | 0 | 0 | 6,412.08 |
| Dissemination | 0 |  |  | 2,000 | 170.17 | 1,839.91 | 1,000 | 0 | 2,839.91 |
| Consumables | 100 |  | 100 | 500 |  | 600 | 300 | 0 | 900.00 |
|  |  |  |  |  |  | Underspend (budget for mini-project) : |  |  | £19,687.43 |

Submitted by Mark Norman, Research Technologies Service, Oxford University.